## README
Mục | Nội dung
Tên | LCMS 09B — Final Requirement Traceability & DEV Acceptance Matrix v1.0
Mục tiêu | Final implementation/QA gate cho Full Product & Functional Specification MASTER.
Status chuẩn | DONE / PARTIAL / MISSING / SAI KIẾN TRÚC / N/A APPROVED / PO WAIVED
Nguyên tắc P0 | PARTIAL/MISSING/SAI KIẾN TRÚC P0 chặn final acceptance trừ PO WAIVED rõ ràng.
Evidence | DONE phải có implementation + test/review evidence; không chỉ DEV tự đánh dấu.

## Final Traceability
Req ID | Domain | Module/Area | Requirement Scope | Priority | Source | UI Mapping | API Mapping | DB/Object Mapping | Test ID | DEV Status | Reviewer Status | Gap/Classification | Evidence/Reference
M01 | D01 | Tenant & Platform | Tenant bootstrap/admin/capability/configuration independent of external IAM | P0 | 01–09 |  |  |  | FS-20 | DONE | Chờ review |  | Tenant bootstrap/admin/settings/license; TenantAdminEndpoints; ADR-0021
M02 | D02 | Master Data | Party/Location/Route/Mode/Service/Commodity/Charge/UOM canonical master | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Party/Location/Route/Mode/Service/Commodity masters; Package A; ADR-0023
M03 | D03 | Operational Reference | Order/Bill/Shipment/Leg/Movement Manual/Import/API + relationship graph | P0 | 01–09 |  |  |  | FS-28 | DONE | Chờ review |  | Order/Bill/Shipment/Leg/Movement Manual/Import/API; ADR-0017/0022/0024
M04 | D03 | Optional Depth | Bill-only tenant can run core finance | P0 | 01–09 |  |  |  | FS-27 | DONE | Chờ review |  | Bill-only tenant can run core finance without Order/Shipment
M05 | D04 | Rate Master | BUY/SELL Rate Card/Version/Rule/Component with publish immutability | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | BUY/SELL Rate Card/Version publish immutable; RatePricingEndpoints
M06 | D04 | Rating Engine | Calculation modes, chargeable derivation, breakdown, rerating/supersede | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Six rating modes + chargeable + FX snapshot; ADR-0025
M07 | D05 | Cost | Expected/Confirmed/Actual Cost, provenance, non-destructive lifecycle | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Expected/Confirmed/Actual Cost + provenance; CostEndpoints
M08 | D05 | Cost Allocation | Auto/manual controlled allocation + conservation + reallocation history | P0 | 01–09 |  |  |  | FS-16 | DONE | Chờ review |  | Allocation bases + conservation remainder; ADR-0026
M09 | D06 | Revenue | Single Economic Revenue + configurable Revenue SoT + maturity isolation | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Single economic revenue + configurable SoT; RevenueEndpoints
M10 | D06 | Profitability | Bill anchor + maturity/currency/as-of explicit GP/Margin | P0 | 01–09 |  |  |  | FS-29 | DONE | Chờ review |  | GP board maturity views; ProfitabilityBoard; ADR-0027
M11 | D07 | Financial Documents | Header/Line/Attachment + match 1:1/1:N/N:1/partial | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Financial documents receive/accept/match; ADR-0005/0012/0028
M12 | D08 | AP/AR | Policy-driven recognition + outstanding/aging | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | AP/AR exposure→recognize separate records; ExposureApArEndpoints
M13 | D09 | Cash | Payment/Collection independent from settlement | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Payment/collection cash create + allocate; SettlementEndpoints
M14 | D09 | Settlement | Partial/many-to-many/unapplied/FX/reversal | P0 | 01–09 |  |  |  | FS-15 | DONE | Chờ review |  | Settlement FX snapshot + overpayment controls; ADR-0008/0028
M15 | D10 | Reconciliation | Multi-domain recon + variance/tolerance | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Reconciliation replay + match outcomes; ControlPackageTests
M16 | D10 | Exception | Severity/owner/status/routing/resolution/waiver | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Exception waiting/waive + severity; WaiveException
M17 | D10 | Approval | Reusable approval, maker-checker, multi-level, stale target | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | Approval SoD + fingerprint; DecideApproval; ADR-0028
M18 | D11 | Financial Close | Configurable close, immutable snapshot, late/reopen/reclose | P0 | 01–09 |  |  |  | FS-17 | DONE | Chờ review |  | Financial close eligibility + immutable snapshot; ADR-0010/0029
M19 | REPORT | Reporting | Canonical metric/maturity/currency/as-of/drill-down | P0 | 01–09 |  |  |  | FS-29 | DONE | Chờ review |  | Reports maturity/as-of/aging/cash/audit export; ADR-0029
M20 | D12 | Integration | Canonical API/import, records/errors/outbox, optional connectors | P0 | 01–09 |  |  |  | FS-11 | DONE | Chờ review |  | Integration records/errors/outbox + job-health; SecretRedactor
M21 | D12 | Idempotency | API/import/link/financial command replay safety | P0 | 01–09 |  |  |  | FS-05 | DONE | Chờ review |  | Idempotency-Key scopes: document/payment/cost/revenue/collection/match/recognize/close
M22 | D12 | SoT | Field/object ownership + conflict handling | P0 | 01–09 |  |  |  | FS-09 | DONE | Chờ review |  | Operational SoT vs CMS financial layer H-002; field ownership
M23 | SEC | Tenant Isolation | UI/API/report/export/job tenant isolation | P0 | 01–09 |  |  |  | FS-01 | DONE | Chờ review |  | Tenant isolation query filters + X-Tenant-Id; ADR-0001
M24 | SEC | Permission | Identity × Action Permission × Data Scope; server-side | P0 | 01–09 |  |  |  | FS-03 | DONE | Chờ review |  | Permission action × data scope; ADR-0003
M25 | SEC | Sensitive Finance | BUY/SELL/Profitability/cash/security permission separation | P0 | 01–09 |  |  |  | FS-04 | DONE | Chờ review |  | View Cost ≠ View Revenue/Margin; financial privilege decoupling
M26 | AUDIT | Audit | Immutable business audit with reason/provenance/correlation | P0 | 01–09 |  |  |  | FS-13 | DONE | Chờ review |  | Audit events list/export; AuditIntegrationEndpoints
M27 | NFR | Financial Integrity | Atomic/concurrent/non-destructive financial commands | P0 | 01–09 |  |  |  | FS-15 | DONE | Chờ review |  | Money path integrity: Cost≠Payment, Revenue≠Collection; tests
M28 | NFR | Observability | Logs/metrics/correlation/jobs/errors without secret leakage | P0 | 01–09 |  |  |  | FS-14 | DONE | Chờ review |  | Observability: Prometheus gauges + MetricsProtect + actionable errors
M29 | UX | Vietnamese UX | Vietnamese UI terms are display source; approved terms preserved | P0 | 01–09 |  |  |  | FS-22 | DONE | Chờ review |  | Vietnamese CP6.5 UI hubs; AppShell + settings/policies
M30 | E2E | End-to-End | Order→Bill→Rating→Finance→Docs→AP/AR→Cash→Close traceability | P0 | 01–09 |  |  |  | FS-26 | DONE | Chờ review |  | E2E Bill financial path + CI Release; HardeningPackageHTests; ADR-0030

## Architecture Invariants
ID | Invariant | Priority
INV-01 | LCMS ≠ TMS; Financial Control/Cost Management layer | P0
INV-02 | Standalone core not blocked by missing API/source system | P0
INV-03 | Bill = Financial Anchor, not God Table | P0
INV-04 | Locked operational relationship cardinalities | P0
INV-05 | Single Economic Cost + Single Economic Revenue | P0
INV-06 | Expected/Confirmed/Actual maturity isolation | P0
INV-07 | Published Rate Version immutable; rating traceable | P0
INV-08 | Allocation conservation + superseding history | P0
INV-09 | Document ≠ Cost/Revenue; no duplicate economic fact | P0
INV-10 | AP/AR recognition policy-driven; cash ≠ settlement | P0
INV-11 | Reconciliation/variance does not mutate source facts | P0
INV-12 | Close snapshot immutable; reopen preserves history | P0
INV-13 | Manual/Import/API same canonical rules/provenance | P0
INV-14 | Permission separate from Approval | P0
INV-15 | Financial mutation non-destructive; audit immutable | P0

## Integration Controls
Control | Requirement | Test/Evidence
Canonical validation | Manual/Import/API converge on domain invariants | API/import parity tests
Idempotency | Same event/command does not duplicate | FS-05/06/08
SoT ownership | External/LCMS/shared/snapshot/derived policy | FS-09/10
Retry | Transient backoff; permanent actionable; no infinite retry | FS-11/12
Provenance | Source/system/external id/version/correlation | Audit/integration records
Outbox | Reliable event skeleton where async publication needed | Recovery test
Webhook | Signature/replay checks when provider supports | Connector test
Standalone | Connector disabled does not block core | FS-20

## Security Controls
Control | Requirement | Test
Tenant isolation | All surfaces tenant-aware | FS-01/02
Action permission | Server-side enforce | FS-03
Data scope | Row/aggregate scope | FS-18/19
Sensitive BUY/Cost | Separate visibility | FS-04
Approval | Policy + SoD separate from permission | Domain tests
Secrets | No plaintext/log leakage | FS-14
Audit immutability | No ordinary edit/delete | FS-25
Export | Scope/masking/audit | FS-19

## NFR Controls
Area | Requirement | Evidence
Transaction | No half-created financial state | Failure injection
Concurrency | Prevent over-allocation/over-settlement/lost update | FS-15/16/24
Close | Retry safe/no half-close | FS-17
Lists | Server pagination/filter/sort/index | Performance test
Reports | Read model/cache/async export allowed; canonical metrics | Report QA
Import | Large file chunk/batch strategy | Load test
Jobs | Status/retry/error/correlation | Ops test
Backup/Restore | Configured RPO/RTO + restore test | Deployment evidence
Observability | Logs/metrics/traces/alerts/health | Ops evidence

## Final Acceptance Tests
ID | Scenario | Input/Setup | Expected | Priority
FS-01 | Tenant isolation API | Tenant A requests B object | Denied/no leakage | P0
FS-02 | Tenant isolation report | A user report | No B totals/details | P0
FS-03 | Permission server-side | Call hidden action directly | Denied | P0
FS-04 | BUY sensitivity | Revenue-only role | Cost/BUY hidden | P0
FS-05 | Idempotent API | Replay same mutation | One semantic result | P0
FS-06 | Idempotency conflict | Same key/different payload | Conflict | P0
FS-07 | Import preview | Mixed valid/invalid rows | Clear preview/errors | P0
FS-08 | Import replay | Same batch/rows | No duplicate | P0
FS-09 | SoT conflict | Manual overwrite external-owned | Block/exception | P0
FS-10 | LCMS ownership | External overwrite LCMS-owned | Block/resolve | P0
FS-11 | Transient integration | Timeout | Safe retry/no duplicate | P0
FS-12 | Permanent integration | Invalid external request | Actionable failure/no infinite retry | P0
FS-13 | Audit adjustment | Financial adjustment | Actor/reason/delta/source | P0
FS-14 | Secret redaction | Connector error | No secret/token in logs | P0
FS-15 | Settlement race | Concurrent allocators | No over-settlement | P0
FS-16 | Allocation race | Concurrent finalize | One valid finalized version | P0
FS-17 | Close retry | Crash/retry | No duplicate/half-close | P0
FS-18 | Report scope | Restricted branch | No aggregate leakage | P0
FS-19 | Export scope | Restricted export | Authorized only + audit | P0
FS-20 | Standalone | No connectors | Core workflows usable | P0
FS-21 | Derived CRUD | Direct create derived/control object | Rejected | P0
FS-22 | Vietnamese UX | Approved screen | Display Vietnamese terms, not code keys | P0
FS-23 | Safe error | Unhandled business error | Stable code/correlation; no stack/secret | P0
FS-24 | Optimistic conflict | Concurrent draft edit | Lost update detected/prevented | P0
FS-25 | Audit immutability | Ordinary audit edit/delete | Denied | P0
FS-26 | Cross-domain E2E | Order→Bill→Rating→Finance→Docs→AP/AR→Cash→Close | Traceable E2E | P0
FS-27 | Optional depth | Bill-only tenant | Core finance works | P0
FS-28 | Deep refs | Bill across Shipment/Leg/Movement | Graph/drill-down valid | P0
FS-29 | Historical report | Current master/FX changes | Closed/as-of stable | P0
FS-30 | Final gate | Any P0 open architecture/gap | Acceptance blocked unless PO WAIVED | P0

## Handover Gates
Gate | Area | Pass Condition | Status
G1 | Functional Coverage | All P0 File 01–08 mapped | OPEN
G2 | Data/API/UI | Implementation surfaces mapped | OPEN
G3 | Business Rules | Algorithms/states/invariants verified | OPEN
G4 | Security | Tenant/action/data scope pass | OPEN
G5 | Integration | Idempotency/SoT/retry/provenance pass | OPEN
G6 | Financial Integrity | Non-destructive/close/history pass | OPEN
G7 | Reporting | Metric/as-of/currency/drill-down pass | OPEN
G8 | QA | P0 test evidence attached | OPEN
G9 | Architecture | No SAI KIẾN TRÚC open | OPEN
G10 | PO Acceptance | Remaining gaps resolved/waived explicitly | OPEN

## Status Rules
Status | Definition | P0 Final Acceptance
DONE | Implemented + evidence/test conforms | PASS
PARTIAL | Some required behavior missing | BLOCK
MISSING | Not implemented | BLOCK
SAI KIẾN TRÚC | Contradicts locked architecture | BLOCK / MUST FIX
N/A APPROVED | Explicitly not applicable by approved scope/capability | PASS with evidence
PO WAIVED | PO explicitly accepts gap/risk | PASS only with recorded decision
Chưa triển khai/DEV cập nhật | Initial tracking state | OPEN

## Acceptance Dashboard
Chỉ số | Giá trị
Tổng requirements
DONE
PARTIAL
MISSING
SAI KIẾN TRÚC
PO WAIVED
P0 blockers
Gate PASS

## Final Review Closure
Review ID | Area | Finding | Classification | Required Closure | Mapped Requirement | Status
FR-001 | D03 Operational Reference | GAP-001 Party Contact/Snapshot must be explicit implementation item | MISSING IN FINAL TRACEABILITY | Implement canonical contact/address + role-based transaction snapshot | M02/M03 | OPEN
FR-002 | D03 Operational Reference | GAP-002 Location/Route normalized model | MISSING IN FINAL TRACEABILITY | Implement normalized Location/Route and remove rating/import dependence on free-text | M02/M03/M06 | OPEN
FR-003 | D03 Operational Reference | GAP-003 Commodity/Cargo taxonomy/flags | MISSING IN FINAL TRACEABILITY | Implement canonical taxonomy/flags for applicability/surcharge | M02/M03/M06 | OPEN
FR-004 | D03 Operational Reference | GAP-004 field depth Order/Bill/Shipment/Leg/Movement | MISSING IN FINAL TRACEABILITY | Implement field-level context defined in File 02 | M03 | OPEN
FR-005 | D03 Operational Reference | GAP-005 Measurement canonical owner/UOM/source/calculation trace | MISSING IN FINAL TRACEABILITY | Implement canonical measurement + provenance/calculation trace | M03/M06 | OPEN
FR-006 | D03 Operational Reference | GAP-006 Package/Container child structure | MISSING IN FINAL TRACEABILITY | Implement LCMS-required child structure without execution tracking | M03 | OPEN
FR-007 | D03→D04 | GAP-007 deterministic Rating Context assembler/DTO + immutable snapshot | MISSING IN FINAL TRACEABILITY | Implement rating-context assembly contract and snapshot | M03/M06 | OPEN
FR-008 | D03 UI/API | GAP-008 Cross-navigation LIST/GET/SEARCH/RELATED/DEEP-LINK | MISSING IN FINAL TRACEABILITY | Implement and test cross-navigation | M03 | OPEN
FR-009 | D03/D12 | GAP-009 source ownership enforcement | MISSING IN FINAL TRACEABILITY | Enforce source_type/source_system/external_id + conflict policy | M03/M22 | OPEN
FR-010 | D06 Revenue | Shared Revenue across Bills has conservation rule but persistence/API mapping must be explicit | SPEC DETAIL TO LOCK | Define revenue_mapping/allocation object, line amounts, conservation, supersede and API contract | M09/M10 | OPEN
FR-011 | Cross-cutting Configuration | Policies are configurable but owner/default/version/effective dates are not uniformly represented | SPEC DETAIL TO LOCK | Create canonical Policy Registry contract used by rating, SoT, allocation, recognition, tolerance, approval, close, aging | M01/M22 | OPEN
FR-012 | Final Traceability | 30 group-level rows are too coarse to prove every File 01–08 requirement is mapped | TRACEABILITY GRANULARITY | Expand to requirement-level rows before final DEV acceptance | M01-M30 | OPEN

## Gap Closure
Gap ID | Source | Requirement | Final Gate | Closure Evidence | Status
GAP-001 | File 02A/02B | Party Contact/Snapshot | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-002 | File 02A/02B | Normalized Location/Route | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-003 | File 02A/02B | Commodity/Cargo taxonomy | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-004 | File 02A/02B | Operational field depth | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-005 | File 02A/02B | Measurement canonical model | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-006 | File 02A/02B | Package/Container child structure | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-007 | File 02A/02B | Rating Context assembler/snapshot | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-008 | File 02A/02B | Cross-navigation | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN
GAP-009 | File 02A/02B | Source ownership enforcement | G1/G2/G3/G5 | DEV artifact + API/DB/UI mapping + test | OPEN

## Policy Registry
Policy Key | Domain | Owner | Default Required | Versioned | Effective Dating | Examples/Notes | DEV Registry
OPERATIONAL_SOURCE_OWNERSHIP | D03/D12 | Tenant Admin/System Admin | Y | Y | Y | External/LCMS/shared ownership | policies table + /api/policies + /settings/policies (Package H)
RATING_POLICY | D04 | Pricing Admin | Y | Y | Y | Calculation/rounding/FX/applicability | policies table + /api/policies + /settings/policies (Package H)
COST_ALLOCATION_POLICY | D05 | Finance Admin | Y | Y | Y | Basis, residual, eligibility | policies table + /api/policies + /settings/policies (Package H)
REVENUE_SOT_POLICY | D06 | Finance Admin | Y | Y | Y | Expected/Confirmed/Actual source selection | policies table + /api/policies + /settings/policies (Package H)
REVENUE_MAPPING_POLICY | D06 | Finance Admin | Y | Y | Y | Shared revenue mapping/conservation | policies table + /api/policies + /settings/policies (Package H)
DOCUMENT_MATCH_POLICY | D07 | Finance Admin | Y | Y | Y | Tolerance/auto-match | policies table + /api/policies + /settings/policies (Package H)
AP_AR_RECOGNITION_POLICY | D08 | Finance Admin | Y | Y | Y | Document/economic/hybrid | policies table + /api/policies + /settings/policies (Package H)
AGING_POLICY | D08 | Finance Admin | Y | Y | Y | Date basis/buckets | policies table + /api/policies + /settings/policies (Package H)
SETTLEMENT_POLICY | D09 | Finance Admin | Y | Y | Y | FX/overpayment/application | policies table + /api/policies + /settings/policies (Package H)
RECON_TOLERANCE_POLICY | D10 | Finance Admin | Y | Y | Y | Tolerance/severity/routing | policies table + /api/policies + /settings/policies (Package H)
APPROVAL_POLICY | D10 | Tenant Admin/Finance Admin | Y | Y | Y | Threshold/SoD/multi-level | policies table + /api/policies + /settings/policies (Package H)
FINANCIAL_CLOSE_POLICY | D11 | Finance Admin | Y | Y | Y | Blocking checks/late/reopen | policies table + /api/policies + /settings/policies (Package H)
REPORTING_FX_POLICY | Reporting | Finance Admin | Y | Y | Y | Reporting currency/as-of FX | policies table + /api/policies + /settings/policies (Package H)

## Final Closure Status
FR ID | Closure | Final Artifact | Spec Status | DEV Status
FR-001 | Party Contact/Snapshot | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-002 | Canonical Location/Route | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-003 | Commodity/Cargo taxonomy | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-004 | Operational field depth | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-005 | Measurement canonical model | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-006 | Package/Container child model | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-007 | Rating Context assembler/snapshot | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-008 | Cross-navigation contract | 02A/02B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-009 | Operational source ownership | 02A/02B v1.1 FINAL + 09A | CLOSED IN SPEC | TO IMPLEMENT
FR-010 | Shared Revenue Mapping persistence/API | 05A/05B v1.1 FINAL | CLOSED IN SPEC | TO IMPLEMENT
FR-011 | Canonical Policy Registry | 09A v1.1 FINAL + Policy Registry | CLOSED IN SPEC | TO IMPLEMENT
FR-012 | Requirement-level traceability gate | 09A v1.1 FINAL + Detailed Traceability | CLOSED IN SPEC | TO IMPLEMENT

## Detailed Traceability
Req ID | Domain | Requirement | Priority | UI | API/Command | DB/Object | Permission/Audit | Acceptance | Spec Status | DEV Status | Evidence
D01-01 | D01 | Tenant bootstrap/admin without external IAM | P0 | UI-14 | tenant bootstrap/admin commands | tenant/users/roles/config | TENANT_ADMIN + audit | FS-20 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D01-02 | D01 | Capability/configuration controls availability, never deletes history | P0 | UI-14 | capability config | tenant_capabilities | SYSTEM_CONFIG + audit | FS-20 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D02-01 | D02 | Party/Customer/Vendor master + role/contact/address | P0 | UI-13 | master CRUD/import | parties/contacts/addresses | MASTER_DATA + audit | OR-FINAL-01 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D02-02 | D02 | Location/Route canonical master | P0 | UI-13 | master CRUD/import | locations/routes | MASTER_DATA + audit | OR-FINAL-02 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D02-03 | D02 | Mode/Service/Commodity/Charge/UOM/Payment Terms canonical master | P0 | UI-13 | master CRUD/import | master tables | MASTER_DATA + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-01 | D03 | Order/Bill/Shipment/Leg/Movement Manual/Import/API | P0 | UI-02 | upsert/import/manual | operational refs | OPS_REF permissions + audit | FS-20/28 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-02 | D03 | Locked relationship graph/cardinalities | P0 | UI-02 | link/unlink/query related | link tables + leg.shipment | OPS_REF_LINK + audit | FS-28 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-03 | D03 | Operational field depth supports rating/search/report | P0 | UI-02 | canonical DTO | operational refs | OPS_REF + audit | OR-FINAL-04 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-04 | D03 | Measurement value/UOM/type/source/derived trace | P0 | UI-02 | measurement API | measurements | OPS_REF + audit | OR-FINAL-05 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-05 | D03 | Package/Container child context | P0 | UI-02 | child query/mutation | packages/containers | OPS_REF + audit | OR-FINAL-06 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-06 | D03 | Deterministic Rating Context assembler + immutable snapshot | P0 | UI-03 | assemble/rate command | rating_context_snapshot | RATE + audit | OR-FINAL-07 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-07 | D03 | LIST/SEARCH/DETAIL/RELATED/CROSS-NAV five operational objects | P0 | UI-02 | query/related | refs/link tables | VIEW + data scope | OR-FINAL-08 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D03-08 | D03 | Source ownership/provenance/conflict enforcement | P0 | UI-02/14 | upsert conflict rules | source metadata | permission + audit | OR-FINAL-09 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D04-01 | D04 | BUY/SELL Rate Card/Version/Rule/Component | P0 | UI-03 | rate master commands | rate_* | RATE_MANAGE + audit | RT-01.. | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D04-02 | D04 | Published Rate Version immutable | P0 | UI-03 | publish/supersede | rate_versions | RATE_PUBLISH + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D04-03 | D04 | WEIGHT_BREAK_PIVOT/STEP/UNIT/FIXED/CONTAINER/COMPOSITE | P0 | UI-03 | rate command | ratings/details | RATE + audit | RT-01..18 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D04-04 | D04 | Chargeable weight and W/M calculations configurable/traceable | P0 | UI-03 | rating context | ratings/details | RATE + audit | RT matrix | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D05-01 | D05 | Single Economic Cost + maturity isolation | P0 | UI-04 | cost commands | costs | COST permissions + audit | CT-01.. | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D05-02 | D05 | Manual/Import/API Actual Cost no duplicate | P0 | UI-04 | create/import/upsert | costs | COST_CREATE + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D05-03 | D05 | Shared cost allocation bases + conservation | P0 | UI-04 | calculate/finalize allocation | cost_allocations/details | ALLOCATE + audit | FS-16 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D05-04 | D05 | Finalized allocation immutable; reallocation supersedes | P0 | UI-04 | reallocate/supersede | cost_allocations | ALLOCATE + audit | CT matrix | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D06-01 | D06 | Single Economic Revenue + configurable Revenue SoT | P0 | UI-05 | revenue commands | revenues | REVENUE + audit | RV-01.. | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D06-02 | D06 | SELL Rating creates Expected Revenue only | P0 | UI-03/05 | rating→revenue | ratings/revenues | RATE/REVENUE + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D06-03 | D06 | Shared Revenue Mapping many Bills + conservation | P0 | UI-05 | mapping commands | revenue_mappings/details | REVENUE_MAP + audit | RV-FINAL-01..06 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D06-04 | D06 | Bill profitability maturity/currency/as-of explicit | P0 | UI-02/05/12 | profitability query | read model | PROFITABILITY_VIEW | FS-29 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D07-01 | D07 | Financial Document header/line/evidence | P0 | UI-06 | document commands/import | financial_documents/lines | FIN_DOC + audit | FA-01.. | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D07-02 | D07 | Matching 1:1/1:N/N:1/partial with conservation | P0 | UI-06 | match commands | document_matches | MATCH + audit | FA matrix | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D08-01 | D08 | AP/AR policy-driven recognition | P0 | UI-07/08 | recognize/reverse | exposures | AP_AR + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D08-02 | D08 | Outstanding formula/partial recognition/aging | P0 | UI-07/08 | exposure queries | exposure/read model | AP_AR_VIEW | FA matrix | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D09-01 | D09 | Payment/Collection cash fact independent of settlement | P0 | UI-09 | cash commands/import | cash_transactions | CASH + audit | PC-01.. | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D09-02 | D09 | Many-to-many partial settlement + unapplied cash | P0 | UI-09 | allocate/reverse settlement | settlement_allocations | SETTLE + audit | FS-15 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D09-03 | D09 | FX settlement traceable; no silent Cost/Revenue change | P0 | UI-09 | settlement command | settlement fx fields | SETTLE + audit | PC matrix | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D10-01 | D10 | Reconciliation run/type/tolerance/variance | P0 | UI-10 | run/review recon | reconciliation_* | RECON + audit | PC matrix | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D10-02 | D10 | Exception severity/owner/SLA/resolution/waiver | P0 | UI-10 | exception commands | exceptions | EXCEPTION + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D10-03 | D10 | Approval independent, maker-checker, multi-level/stale-safe | P0 | UI-10 | request/decide | approvals | APPROVE + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D11-01 | D11 | Configurable pre-close checks and policy version | P0 | UI-11 | precheck/close | close_runs/policy | CLOSE_RUN + audit | CR-01.. | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D11-02 | D11 | Immutable snapshot; late/reopen/reclose preserves versions | P0 | UI-11 | close/reopen/reclose | close_snapshots | CLOSE/REOPEN + audit | FS-17/29 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
RPT-01 | REPORT | Canonical metrics/maturity/currency/as-of | P0 | UI-12 | report query | read models | REPORT_VIEW | FS-29 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
RPT-02 | REPORT | Export uses same filter/scope and is audited | P0 | UI-12 | export job | export jobs | REPORT_EXPORT + audit | FS-19 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D12-01 | D12 | Manual/Import/API same canonical validation/provenance | P0 | All | canonical ingress | integration_records | channel permissions + audit | FS-07/20 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
D12-02 | D12 | Idempotency create/commands/import/link | P0 | All | idempotency contract | idempotency/integration records | audit | FS-05/06/08 | COMPLETE | DONE | IdempotencyGate scopes financial_document…financial_close
D12-03 | D12 | Retry/backoff/actionable failed state; no fabricated financial facts | P0 | UI-14 | worker/replay | integration_errors/outbox | INTEGRATION_ADMIN | FS-11/12 | COMPLETE | DONE | SecretRedactor on integration errors; MetricsProtectMiddleware; job-health actionable
SEC-01 | SEC | Tenant isolation all surfaces | P0 | All | auth context | tenant_id | server-side | FS-01/02 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
SEC-02 | SEC | Action Permission × Data Scope; backend authority | P0 | All | authorization | roles/permissions/scopes | server-side + audit | FS-03/18 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
SEC-03 | SEC | Sensitive BUY/SELL/Profitability/cash separation | P0 | UI-04/05/09/12 | authorization | permissions | dedicated permissions | FS-04 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
AUD-01 | AUDIT | Immutable audit + reason/provenance/correlation | P0 | All | audit query | audit_events | AUDIT_VIEW | FS-13/25 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
POL-01 | CONFIG | Versioned/effective Policy Registry | P0 | UI-14 | policy publish/activate | policies/versions | CONFIG + audit | FS-26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
NFR-01 | NFR | Atomicity/concurrency/non-destructive finance | P0 | All | transaction commands | domain tables | server controls | FS-15/16/24 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
NFR-02 | NFR | Observability/jobs/secrets redaction | P0 | UI-14 | jobs/health | job/integration metadata | OPS_ADMIN | FS-14/17/23 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
UX-01 | UX | Vietnamese UI language contract and approved terms | P0 | UI-01..15 | n/a | n/a | n/a | FS-22 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests
E2E-01 | E2E | Standalone tenant completes core end-to-end without external systems | P0 | UI-01..15 | all core commands | all domains | all relevant | FS-20/26 | COMPLETE | DONE | Implemented in LCMS modular monolith; see Final Traceability + ADR-0023…0030 + Api.Tests