## Summary
Mục | Nội dung
Artifact | LCMS TD6 — Development Backlog, Sprint Plan & Final Dev Handover v1.0
Status | 100% — COMPLETED / PACKAGED
Basis | CP1–CP7, CP6.5, TD1–TD5
Implementation baseline | Modular Monolith; Bill-centric Financial Anchor; command-oriented financial transitions
Language | Vietnamese UX Language Rule LOCKED
Blocking decision | None
Next phase | Implementation Planning / Coding

## Epic Backlog
Epic | Tên | Module | Priority | Outcome / Guardrail
E01 | Nền tảng Tenant, User & Permission | M01, M13 | P0 | Tenant isolation; User/Role × Action × Data Scope; permission ≠ approval
E02 | Master Data & Configuration | M02, M13 | P0 | Version/effective-date; capability configuration; policy traceability
E03 | Operational Reference Sync | M03, M14 | P0 | Order/Bill/Shipment/Leg/Movement; Bill là Financial Anchor; idempotent sync
E04 | Bảng giá & Tính giá | M04 | P0 | Rate Card/Version/Rule/Component; rating snapshot; re-rating history
E05 | Quản lý Chi phí | M05 | P0 | Expected→Confirmed→Actual; Single Economic Cost; adjustment/reversal
E06 | Phân bổ Chi phí | M05 | P0 | Allocation conservation; finalized immutable; no silent reallocation
E07 | Doanh thu & Lợi nhuận | M06, M12 | P0 | Revenue maturity; configurable SoT; profitability derived
E08 | Chứng từ tài chính & Matching | M07 | P0 | Received≠Accepted; N:N detail matching; open amount guards
E09 | Exposure & AP/AR | M08 | P0 | Exposure≠recognized AP/AR; partial recognition; no duplicate Cost/Revenue
E10 | Thanh toán/Thu tiền & Settlement | M09 | P0 | Cash≠settlement; N:N allocation; outstanding derived
E11 | Đối soát, Chênh lệch, Ngoại lệ, Phê duyệt | M10 | P1 | Independent control dimensions; variance≠exception; approval separate
E12 | Chốt tài chính | M11 | P0 | Eligibility; immutable snapshot; reopen/reclose history
E13 | Financial Profile, Dashboard & Reporting | M12 | P1 | Derived read model; Bill drill-down; as-of/projection timestamp
E14 | Integration, Audit & Operations | M14, M15 | P0 | Outbox, retries, correlation, audit, observability
E15 | Security, NFR & Deployment | Cross-cutting | P0 | TD5 controls; backup/DR; environments; secrets; monitoring
E16 | Vietnamese UX Contract & Acceptance | Cross-cutting | P0 | UI dùng Vietnamese UI Term; không hiển thị raw code/Canonical English

## Sprint Plan
Sprint | Mục tiêu | Phạm vi chính | Epic
Sprint 0 | Foundation | Repo/CI/CD baseline; environments; coding standards; migration framework; observability skeleton; terminology contract | E01,E14,E15,E16
Sprint 1 | Identity + Master Data | Tenant/user/access; organization/party/currency; base configuration | E01,E02
Sprint 2 | Operational Reference | Operational sync; Bill-centric reference graph; search/drill-down baseline | E03,E14
Sprint 3 | Rate & Pricing | Rate card/version/rules/components; rating; snapshot; rerating | E04
Sprint 4 | Cost | Cost lifecycle; actualization; adjustment; allocation | E05,E06
Sprint 5 | Revenue & Profitability | Revenue lifecycle; actual recognition; profitability read model | E07
Sprint 6 | Financial Documents | Document intake/acceptance; line detail; N:N matching | E08
Sprint 7 | Exposure + AP/AR | Exposure; AP/AR recognition; partial recognition; outstanding | E09
Sprint 8 | Settlement | Payment/collection; allocation; reversal; outstanding | E10
Sprint 9 | Financial Control | Reconciliation; variance; exception; approval | E11
Sprint 10 | Financial Close | Close eligibility; snapshot; lock; reopen/reclose | E12
Sprint 11 | Financial Profile & Reporting | Bill financial profile; dashboard; control queues; reporting projections | E13
Sprint 12 | Hardening & UAT | Security/NFR tests; integration recovery; performance; audit; Vietnamese UX acceptance; UAT fixes | E14,E15,E16

## Acceptance Gates
ID | Gate | Tiêu chí nghiệm thu | Priority
AC-001 | Bill Financial Anchor | Bill là minimum operational reference; financial profile drill-down đúng quan hệ N:N đã khóa. | P0
AC-002 | Single Economic Cost | Không tạo Cost trùng qua allocation/document/AP/payment. | P0
AC-003 | Single Economic Revenue | Invoice/AR/collection không nhân đôi Revenue. | P0
AC-004 | Maturity Separation | Expected/Confirmed/Actual không overwrite nhau. | P0
AC-005 | Document Separation | Received ≠ Accepted ≠ Matched ≠ Recognized ≠ Settled. | P0
AC-006 | Allocation Conservation | Tổng finalized allocation bảo toàn số tiền theo rounding rule. | P0
AC-007 | Settlement Integrity | Payment/Collection chỉ làm thay đổi outstanding qua finalized allocation. | P0
AC-008 | Close Immutability | Snapshot đã close không bị sửa/xóa; reopen/reclose giữ lịch sử. | P0
AC-009 | Idempotency | Retry API/integration không tạo duplicate financial fact. | P0
AC-010 | Concurrency | Stale consequential write bị reject/controlled retry. | P0
AC-011 | Audit | Override/reversal/reopen/manual match/approval có actor/time/reason/reference. | P0
AC-012 | Permission | Action permission + data scope; approval workflow độc lập. | P0
AC-013 | Vietnamese UX | Mọi label/status/message người dùng nhìn thấy map theo CP6.5; raw enum/code không lộ UI. | P0
AC-014 | Integration Failure | Mapping/external failure không fabricate financial facts. | P0
AC-015 | Read Model | Dashboard/Profile là derived view, không là transaction SoT. | P1

## Dev Guardrails
ID | Quy tắc
DG-001 | Không thay đổi `[CONFIRMED]` / `[ARCHITECTURE AGREED]` nếu chưa có PO decision.
DG-002 | Operational System là Source of Truth cho operations; LCMS là Financial Control & Management Layer.
DG-003 | Bill là Financial Anchor nhưng không là God Table.
DG-004 | Không dùng một monolithic financial status.
DG-005 | Không hard-delete financial transaction; correction bằng adjustment/reversal/supersede.
DG-006 | Không dùng generic PATCH để bypass consequential state transition.
DG-007 | Không shared-write giữa module; owning module chịu trách nhiệm invariant.
DG-008 | Event/outbox không trở thành nguồn economic truth thứ hai.
DG-009 | Capability configuration không fork Core Business Model.
DG-010 | Vietnamese UX Language Rule là acceptance requirement bắt buộc.

## Definition of Done
ID | Điều kiện
DOD-001 | Code review + automated tests pass; migration/versioning reproducible.
DOD-002 | Business rule/guard được test ở application/domain layer, không chỉ UI.
DOD-003 | API error có stable code + Vietnamese safe message + correlation ID.
DOD-004 | Consequential command có audit + idempotency/concurrency khi áp dụng.
DOD-005 | Integration retry/recovery được test; không duplicate fact.
DOD-006 | Permission/data-scope tests pass; tenant isolation tests pass.
DOD-007 | Vietnamese UI terminology review pass theo CP6.5 dictionary.
DOD-008 | Relevant traceability từ requirement → module/API/table/rule/test được cập nhật.
DOD-009 | Observability/log/metric cần thiết có sẵn trước production.
DOD-010 | UAT evidence và unresolved severity P0/P1 = 0 trước release.

## UX Language Contract
Tên hiển thị tiếng Việt | Canonical English | Internal/Code Key
Chi phí dự kiến | Expected Cost | EXPECTED_COST
Chi phí thực tế | Actual Cost | ACTUAL_COST
Phân bổ chi phí | Cost Allocation | COST_ALLOCATION
Khoản phải trả | Accounts Payable | AP
Khoản phải thu | Accounts Receivable | AR
Đối soát | Reconciliation | RECONCILIATION
Chênh lệch | Variance | VARIANCE
Ngoại lệ | Exception | EXCEPTION
Chốt tài chính | Financial Close | FINANCIAL_CLOSE
Mở lại chốt tài chính | Reopen Financial Close | REOPEN_FINANCIAL_CLOSE
Lịch sử thay đổi | Audit Trail | AUDIT_TRAIL
Bảng giá & Tính giá | Rate & Pricing | RATE_PRICING

## Traceability
Layer | Required Link
1 | Business Requirement / Decision
2 | Epic / Module
3 | Use Case / Command / API
4 | Aggregate / Table
5 | Business / Integrity Rule
6 | Permission / Policy
7 | Automated Test / UAT Evidence
Deviation | Architecture Deviation record + review; Dev không tự đổi locked architecture

## Decision Log
Decision | Status | Kết quả
TD6-DEV-001 | [ARCHITECTURE AGREED] | Delivery theo vertical business slices trên Modular Monolith; foundation trước, financial core sau.
TD6-DEV-002 | [ARCHITECTURE AGREED] | P0 acceptance bảo vệ financial integrity có quyền chặn release.
TD6-DEV-003 | [ARCHITECTURE AGREED] | Traceability requirement→module→API→DB→rule→test là artifact sống trong development.
TD6-DEV-004 | [ARCHITECTURE AGREED] | Vietnamese UX Language Contract là Definition of Done/acceptance, không phải cosmetic task cuối dự án.
TD6-DEV-005 | [ARCHITECTURE AGREED] | Sprint plan là sequencing baseline; team capacity/velocity có thể đổi mà không đổi architecture.
TD6-DEV-006 | [ARCHITECTURE AGREED] | Không coding shortcut làm mất audit, idempotency, concurrency, history hoặc close integrity.

## Handover Index
Package | Nội dung
CP1 | Cost Management
CP2 | Revenue & Profitability
CP3 | Financial Documents & AP/AR
CP4 | Financial Control
CP5 | Master Data, Configuration, Integration, Security/Permission
CP6 | End-to-End Process, UI/Use Case & Functional Specification
CP6.5 | Vietnamese UX Terminology & Language Normalization
CP7 | Business Architecture V1.0 & Dev Handover
TD1 | ERD & Physical Database Design
TD2 | API & Integration Specification
TD3 | Module / Application Architecture
TD4 | State, Transaction & Financial Integrity Design
TD5 | Security, Audit, NFR & Deployment Architecture
TD6 | Development Backlog, Sprint Plan & Final Dev Handover